Sample Scope and Sequence of Professional Learning Engagement

| Curriculum or Content Area | i-Ready Classroom Mathematics (K–8 Mathematics) |  |  |
| --- | --- | --- | --- |
| Type of Professional Learning | Initial Implementation (Year 1) |  |  |
| Total Cost Range | - Less than $50,000 - $50,000 - $100,000 - $100,001 - $500,000 |  | - $500,001 - $1,000,000 - $1,000,000+ |
| District Context | Large urban/suburban district. 31,560 students across 38 schools district-wide. The engagement serves 24 elementary schools and 5 junior highs using i-Ready Classroom Mathematics (~1,054 teachers), plus instructional coaches and building/district leaders. First year of K–8 i-Ready Classroom Mathematics implementation, delivered as a phased rollout (Waves 1 & 2, Wave 3, and Wave 4). Overall goal: teachers apply instructional practices centered on meaningful discourse and student ownership of math ideas; teachers and leaders understand the program’s instructional design and supporting resources to build a discourse-rich math classroom; and leaders align practice with the program’s instructional philosophy and determine steps to monitor and support implementation. |  |  |

Sample Scope and Sequence

| Timing (you may choose to use specific days/months or frequency) | Participants | Name of PL (either specific workshop title, coaching, etc) and format( Virtual, in-person, hybrid) | Description |
| --- | --- | --- | --- |
| Apr 22 – May 16, 2024 (11 sessions; 7–8) | Waves 1 & 2: K–6 math teachers and 7–8 instructional coaches; school leaders as able | Introducing the i-Ready Classroom Mathematics Program (Optional/Recommended) Facilitated PD Session – In-Person | Explore the structure and key instructional features of the program; describe how components support meaningful student learning; and access print & digital resources to prepare ahead of back-to-school. |
| May 16, 2024 | Leaders from each elementary school and junior high; district leaders | Leading an i-Ready Classroom Mathematics Implementation I Facilitated PD Session – In-Person | Reflect on current practice and set implementation goals; identify essential program components that support implementation; and use the Top Teacher Actions Look Fors tool to monitor implementation health. |
| July 18, 2024 (16 sessions) | Waves 1 & 2: K–1 and 2–6 elementary teachers, 7–8 junior high teachers, and instructional coaches; school leaders as able | Preparing to Teach i-Ready Classroom Mathematics with Integrating Digital Resources Facilitated PD Session – In-Person (+ self-led Online Educator Learning Course) | Teach Lesson 0 to establish a classroom where students make meaning of mathematics through purposeful conversation; use the Teacher’s Guide to plan and implement instruction; motivate and prepare students for the Diagnostic; and use digital components for instruction, practice, assessment, and differentiation. Follow-up Collaborative Learning Extension: Establishing Routines Using Lesson 0. |
| Aug 28, 2024 (AM walkthroughs / PM sessions) | Waves 1 & 2: K–8 math teachers; instructional coaches; school leaders as able | Developing Mathematical Thinkers through Instructional Routines with Personalized Instruction Orientation Facilitated PD Session – In-Person (+ self-led OEL course) | Draw connections between the Try–Discuss–Connect routine and mathematical practices; use the routine to develop conceptual understanding through shared student thinking, productive struggle, and authentic discourse; and learn how i-Ready Personalized Instruction complements teacher-led instruction. |
| Aug 28, 2024; Jan 16 & Feb 26, 2025 | K–8 leaders from each elementary school and junior high | Leadership Look Fors Visit Meeting – In-Person | Define the observable markers of a successful implementation and use them to analyze their own implementation; conduct classroom visits using i-Ready Classroom Mathematics Look Fors and create actionable plans to support educators. |
| Oct 9, 2024 | Leaders from each elementary school and junior high; district leaders | Leading an i-Ready Classroom Mathematics Implementation I Facilitated PD Session – In-Person | Reflect on observations from the Leadership Look For Visits; analyze Diagnostic 1 data; and understand the importance of monitoring i-Ready usage. |
| Nov 5 – 25, 2024 (K–1 & 2–6); Jan 28 (JH); Feb 26 (ASCILLS) | Waves 1 & 2: K–6 elementary and 7–8 junior high teachers; instructional coaches; school leaders as able | Tailored Support Facilitated PD Session – In-Person | Select from opportunities designed with leaders and coaches based on implementation goals and educator needs: Try–Discuss–Connect routine facilitation, differentiation strategies to accelerate learning, pacing support, and meaningful practice opportunities. |
| Jan 24, 2025 | Leaders from each elementary school and junior high; district leaders | Leading an i-Ready Classroom Mathematics Implementation I Facilitated PD Session – In-Person | Analyze Diagnostic 2 data and discuss Typical and Stretch Growth; reflect on what is going well and what to adjust for the second half of the year. |
| Dec 3 – 12, 2024 (Wave 3) | Wave 3: K–1 and 2–6 math teachers; instructional coaches; school leaders as able | Preparing to Teach i-Ready Classroom Mathematics with Integrating Digital Resources Facilitated PD Session – In-Person (+ self-led Online Educator Learning Course) | Teach Lesson 0 to establish a classroom where students make meaning of mathematics through purposeful conversation; use the Teacher’s Guide to plan and implement instruction; motivate and prepare students for the Diagnostic; and use digital components for instruction, practice, assessment, and differentiation. Follow-up Collaborative Learning Extension: Establishing Routines Using Lesson 0. |
| Feb 26, 2025 (Wave 3; 10 sites) | Wave 3: K–1 and 2–6 math teachers; instructional coaches; school leaders as able | Developing Mathematical Thinkers through Instructional Routines with Personalized Instruction Orientation Facilitated PD Session – In-Person (+ self-led Online Educator Learning Course) | Draw connections between the Try–Discuss–Connect routine and mathematical practices; use the routine to develop conceptual understanding through shared student thinking, productive struggle, and authentic discourse; and learn how i-Ready Personalized Instruction complements teacher-led instruction. |
| March 25 & 28, 2025 (Wave 3) | Wave 3: K–6 math teachers; instructional coaches; school leaders as able | Tailored Support Facilitated PD Session – In-Person | Select from opportunities designed with leaders and coaches based on implementation goals and educator needs: Try–Discuss–Connect routine facilitation, differentiation strategies to accelerate learning, pacing support, and meaningful practice opportunities. |
| April 22, 24 & 29, 2025 (Wave 4) | Wave 4: K–1 and 2–6 math teachers; instructional coaches; school leaders as able | Preparing to Teach i-Ready Classroom Mathematics with Integrating Digital Resources Facilitated PD Session – In-Person (+ self-led Online Educator Learning Course) | Teach Lesson 0 to establish a classroom where students make meaning of mathematics through purposeful conversation; use the Teacher’s Guide to plan and implement instruction; motivate and prepare students for the Diagnostic; and use digital components for instruction, practice, assessment, and differentiation. Follow-up Collaborative Learning Extension: Establishing Routines Using Lesson 0. |
| August 2025 (Wave 4) | Wave 4: K–1 and 2–6 math teachers; instructional coaches; school leaders as able | Developing Mathematical Thinkers through Instructional Routines with Personalized Instruction Orientation Facilitated PD Session – In-Person (+ self-led Online Educator Learning Course) | Draw connections between the Try–Discuss–Connect routine and mathematical practices; use the routine to develop conceptual understanding through shared student thinking, productive struggle, and authentic discourse; and learn how i-Ready Personalized Instruction complements teacher-led instruction. |

Includes any travel related expenses, etc.